The Gardens Network:

Planning Your Community Garden Year

*Suggested activities for Garden Leaders throughout the year:

## January- February

Pre-season planning meetings

• Review last season.

• Verify that all garden leadership positions are filled; recruit needed volunteers.

• Assign tasks to prepare for upcoming season.

• Set dates: Registration, Opening Day, Planting Date, work days, Closing day.

• Set garden social/educational events and contact possible facilitators, e.g., MGVs.

• Review Welcome Packet; make changes as needed.

• If necessary, make plans for special building projects or expansion.

• Plan outreach activities for new and returning gardeners (if needed), e.g., postcards, calls, emails, Facebook.

• Update waiting list.

Share your garden calendar updates with the Gardens Network (contact gardens@communitygroundworks.org).

# March-april

Registration Event(s)

• Contact new and returning gardeners.

• Mail notice of Registration Day (one month prior) to returning gardeners, new gardeners        and wait listed gardeners.

• Prepare for Registration Day.

• Hold Registration Day.

• Update garden contact list.

• Contact Master Gardener Volunteers to help support your garden.

• Call Water Utility if your garden uses fire hydrant for water supply.

• Meet with Garden Leadership Team; most gardens hold monthly meetings.

• Order hay/straw (if needed).

• Submit demographic forms to the Garden Network (contact CGW)

## April-May

Garden Opening

• Prepare for opening day (buy supplies, send reminders).

• Opening Day! And Rain date…

• Meet monthly with Garden Leadership Team.

## May

Spring Water Maintenance

• Turn on water May 1 or later (pipes can freeze – respect weather).

• Set up hoses, water barrels, etc.

• Meet with Garden Leadership Team.

## June, July, & August

Growing Season

• Ensure gardens are planted (reassign plots if needed). Many gardens use June 1st as their “plant by” date.

• Hold regularly scheduled work days to build community and maintain common areas of garden; most gardens hold monthly work days.

• Host social events at your garden.

• Offer educational events at your garden, e.g., gardening skills, cooking skills, theft control, etc. Provide interpreters for non-English speakers.

• Monitor weeds in plots and common areas. Contact gardeners with weedy plots and offer advice, support, ideas. Issue warnings if necessary (may need to reassign plot).

• Meet monthly with Garden Leadership Team.

## September

Fall Water Maintenance

• Turn off Water by September 30:

For hydrants, call Water Utility and return key

For other systems, turn off water and train 1-2 others about process.

• Meet with Garden Leadership Team.

## October

Closing Day

• Send postcards, emails, texts (or calls) and post reminder of Closing Day.

• Prepare for Closing Day: tools, trash bags, etc. as needed.

• Hold Closing Day: remove all garden debris, store tools, clean common spaces.

• Meet with Garden Leadership Team.

## November-December

End of Season Events

• Hold post-season review meeting with leadership team.

• Identify non-returning gardeners.

• Hold Harvest Gathering (potluck) to celebrate season’s bounty.

• Recruit garden leadership for next year and recognize current volunteers!

• Schedule garden leadership team meetings for pre-season (Winter) planning.